## Goals-2020
Date: | Big Picture | Notes | Project | Time Till Completion | Progress Made | Comments
2020-01-06
2020-01-13
2020-01-20
2020-01-27 | Begin work on EEID abstract | For this abstract, I will need to present more confident results. This means verifying my methods as well as working on results. For the manuscript I want to write, I have two goals 1) to study the pangenome of local michigan endemic M. bovis (personal) and 2) to study the accessory genome of reservoirs around the world. | Chapter 1 | T-8 | The work we did this week sets up the foundations for later work.Essentially try to map the data I have with the naming convention that liliana has.
| Statistical Support for Assembler Methodology | In a pangenomic analysis, the better the assemblies we give, the more confident we can be in the final interpretation. In an effort to make the best decision, we need to create an experiment to minimize for standard deviation of QUAST output. This might take the entire week to run successfully, and then some extra time to create the visualization of the results. Use the figure as a supplement later on | Chapter 1 |  | This is stymied by not knowing what type of data we have. I will work this weekend to get this information
| R code to download SRA data | Alongside the research, Liliana instructed me to create a script that can download data from SRA using R. I want to finish this script during this week. Will most likely rely on Rselenium for web scraping potential, make it public from Salvador lab. | Miscellaneous |  | https://github.com/noahaus/SRA_scraper.git | very useful
| MPI4py tutorials | Learn how to use mpi4py module to add parallel computing power to the cluster scripts |  |  | will meet with the people at GACRC | Did you learn this? If yes, worth to write a brief summary (how to for others to learn as well). If not, something to learn at a later stage - not priority but worth to learn
2020-02-03 | Run Assembly configuration on Michigan Data | Run the best Assembler in parallel on all the sequence we have from Michigan | Chapter 1 | T-7 | This will be an end of the week goal, will not stop until I can start running assemblers.
| Download M. bovis data | Use previously developed script to download the global M. bovis database. | Chapter 1 |  | Done and Done, taken from run selector. | Does this mean that you have all Mbovis genomes from NCBI?
| Begin work on IDEAS Internal Grant | Begin the process of writing the two pages necessary to submit to the IDEAS grant. Luckily, after all this research is culminating, I'll have great preliminary results that focus on two scales that M. bovis is apart of. Right now, I want my aims to be 1) Pangenomics of M. bovis host adaptation 2) Phylogenomic/Phylogeographic spread of M. bovis and 3) Transmission of M. bovis through a metapopulation analysis | IDEAS Grant |  | I already have a basic outline but I think I need to be in lock step with Liliana in terms of clear objectives. I chose not to do these aims because they didn't fall under a particular theme of research at the time, and they weren;t well supported by the literature reviews I did at the time. | It seems that you did not pursue these aims for your proposal. Why?
| Further Work on Pangenome review | What is the poangenome concept and how is it beneficial. | Miscellaneous |  | This is a current work in progress, but is being fleshed out now.
| MPI genome assembly script | After the MPI tutorial on the Sapelo2 cluster, develop some programs to speed up genome annotation time | Miscellaneous |  | I did not do this, but I do have resources provided by the GACRC to help in the construction of GACRC scripts. | Did you do this? Same comment as above
2020-02-10 | Genome Annotation and Pangenome Analysis | Use available tools to characterize what is present in the genome assemblies. PIRATE and Roary both can do the pangenome inference, so which one is better? Will have to investigate | Chapter 1 | T-6 | For simplicity sake, I decided to just use Roary. As I understand it, PIRATE can allow relaxed thresholds for what constitutes a gene family, but by the time I was coding my pipeline, I had decided to just use Roary. | Which one is the best? Roary? Why?
2020-02-17 | Assess the Data | Do the results make sense? What do we see in the findings? | Chapter 1 | T-5 | This analysis needed to be reassesed!
| Run Assembly configuration on Global Data | Do the same procedure as in Feb 3rd, but with all reservoirs from around the world. Will potentially take a longer time? | Chapter 1 |  | Was not able to get here yet. I'm learning that science should be an efficient and patient effort, can't be rushed
2020-02-24 | Genome Annotation and Pangenome Analysis | Use available tools to characterize what is present in the genome assemblies (Global). PIRATE and Roary both can do the pangenome inference, so which one is better? Will have to investigate | Chapter 1 | T-4 | For simplicity sake, I decided to just use Roary. As I understand it, PIRATE can allow relaxed thresholds for what constitutes a gene family, but by the time I was coding my pipeline, I had decided to just use Roary.
2020-03-02 | Assess the Data | Do the results make sense? What do we see in the findings? | Chapter 1 | T-3 | This never happened, EEID was cancelled during this time frame
2020-03-09 | Writing EEID abstract | Writing! | Chapter 1 | T-2 | This never happened, EEID was cancelled during this time frame
2020-03-16 | Writing EEID abstract | Writing! | Chapter 1 | T-1 | This never happened, EEID was cancelled during this time frame
UPDATING TIMELINE (SANS COVID-19)
2020-03-23 | Clustering Analysis of Global M. bovis Isolates | Right now we are trying to see what patterns originate in global pangenome data when looking specifically at pe & ppe gene presence and absence. How do they relate to the species in disease systems on differing scales. Incorporating USA, UK, and NZ M. bovis data. | Chapter 1 | T-6
2020-03-30 | Refining IDEAS proposal | Writing! | Chapter 1 | T-5
2020-04-06 | Refining IDEAS proposal | Due this week (April 10th) | Chapter 1 | T-4
2020-04-13 | Analyze Core Genome (Gene Variability and Recombination ) | Reconstruct the analyses done by Phelan et al. 2016 | Chapter 1 | T-3
2020-04-20 | Verify Preliminary Core Genome analysis | Consult Literature and Data to see if the findings truly make sense | Chapter 1 | T-2
2020-04-27 | Beginning Stages of Final Analysis | Depending on the things we notice from the Core Genome and Accessory Genome preliminary results, this should be a natural time to do a pangenome analysis of all global reservoirs & non reservoirs. Keep good documentation and rough notes for eventual manuscrtipt | Chapter 1 | T-1
2020-05-04 | Extract Sequence Data + Data Cleaning | Gather the data from the 3 papers and make sure they are named correctly/ they make sense | Chapter 1 | T-16 | Done Successfully :)
2020-05-11 | Trimming + Assembly + Stats | Trimming Script using trimmomatic. Assembly using SPAdes. Stat creation using QUAST or MultiQC | Chapter 1 | T-15 | Trimming Complete.
| Pangenome Review | Finish first draft. | Chapter 1
2020-05-18 | M. bovis Annotation + Pangenome Inference | Annotation using prokka (buttressed by M. bovis genome file) . Pangenome Inference using Roary. Reservoir specific vs. Non Reservoir. System specific? | Chapter 1 | T-14
2020-05-25 | Aim 1: Accessory Genome Clustering | Hierarchical Clustering (Jaccard dist. + Ward linkage), logistic PCA | Chapter 1 | T-13
2020-06-01 | Aim 2: Selection Pressure + Homologous Recombination | HyPhy, ClonalFrameML + PhiPack or | Chapter 1 | T-12
2020-06-08 | Aim 3: GWAS |  | Chapter 1 | T-11
2020-06-15 | Finish up spare analyses | I'll work as quickly as I can, but if I can't finish something in a week I'll just move on. The things I can't finsih will be done during this time. | Chapter 1 | T-10
2020-06-22 | Finish up spare analyses | I'll work as quickly as I can, but if I can't finish something in a week I'll just move on. The things I can't finsih will be done during this time. | Chapter 1 | T-9
2020-06-29 | Finish up spare analyses | I'll work as quickly as I can, but if I can't finish something in a week I'll just move on. The things I can't finsih will be done during this time. | Chapter 1 | T-8
2020-07-06 | Writing + Lab Chores (MPI documentation & NCBI script) | With the analyses wrapped up, I can write and do some things for the lab. Namely, document some techniques for future use in the lab | Chapter 1 | T-7
2020-07-13 | Writing + Lab Chores (MPI documentation & NCBI script) | With the analyses wrapped up, I can write and do some things for the lab. Namely, document some techniques for future use in the lab | Chapter 1 | T-6
2020-07-20 | Writing + Lab Chores (MPI documentation & NCBI script) | With the analyses wrapped up, I can write and do some things for the lab. Namely, document some techniques for future use in the lab | Chapter 1 | T-5
2020-07-27 | Writing + Lab Chores (MPI documentation & NCBI script) | With the analyses wrapped up, I can write and do some things for the lab. Namely, document some techniques for future use in the lab | Chapter 1 | T-4
2020-08-03 | Prepare for first Submission | Homestrech | Chapter 1 | T-3
2020-08-10 | Prepare for first Submission | Homestrech | Chapter 1 | T-2
2020-08-17 | Submit Manuscript |  | Chapter 1 | T-1